## Slide 1: IMS PROJECT INTRODUCTION

## Slide 2: PURPOSE
The purpose of this project is to provide telecommunication users various multimedia services such as instant messaging, voice and video calls. The interns will be involved in building a client application (desktop or mobile) that requests a service and resource from a deployed IMS server by using key IMS protocols such as SIP, SDP, RTP, H.248, DNS/ENUM and Diameter. This project will use an open-source IMS Core System (www.openimscore.com) for server side. The internship team can use any programming language for developing the client application, preferred Java or C/C++. Agile/Scrum will be used during this project. Sprint length is 2 weeks and the project will complete in 5 Sprints.

## Slide 3: PROJECT PLAN
Sprint 1: Team kickoff; Agile/Scrum training; IT Policy, Company policy, Continuous Integration (CI), GIT & GERRIT; Research IMS basic concepts; Client code structure on Git;
Sprint 2: Research IMS protocols such as SIP, SDP, RTP, H.248, DNS/ENUM and Diameter; Research IMS user and service identities; Deploy Open IMS Core server; Develop client GUI;
Sprint 3: Research registration, basic call setup and release; Develop client application for making and receiving voice calls;
Sprint 4: Extend the client application for making and receiving video calls;
Sprint 5: Re-factor and final demo; project closure;

## Slide 4: REFERENCE
Open IMS Core, https://www.openimscore.com
Segeč, Pavel & Kovacikova, Tatiana. (2012). Implementation of IMS testbeds using open source platforms. Komunikacie. 14. 55-62.
Camarillo, Gonzalo & A. García‐Martín, Miguel. (2007). The 3G IP Multimedia Subsystem (IMS) Merging the Internet and the Cellular Worlds.